## Slide 1: CSIS 2430 Project 2 Plan
Course/Term: CSIS 2430
Project: Project 2
Team: Helen Le, Owen Francy, Mustafa Alrubaye
Start Date: Oct 5th
Due Date: October 25th 2026
Checkpoint/mid-project Date: Oct 18th

## Slide 2: Team & Roles
Team Member | Role | Primary Responsibilities | Availability/notes
Mustafa | Implementation Lead | owns core implementation, integration, and main branch health. | Monday 3:30 - 11 Tuesday 1 - 5 and 7:30 - 11 Wednesday 3:30 - 5 and 10-11 Thursday 1 - 5 and 7:30 - 11 Friday 3:30 - 11 Saturday 3:30 to whenever Sunday 3:30 - 11
Helen | Verification Lead | owns test plan, edge cases, and verification evidence. | (work hours not accounted for) Mon, Wed, Thurs: 12:30 pm - whenever Tues: 12:30 pm - 4:30 pm Fri-Sun: whenever
Owen | Communications Lead | owns report assembly, run instructions, and deliverable packaging. | Mon - Thurs: 12 pm - basically whenever Fri: 9 am - 2 pm Sat: 9 am - 12:30 pm and ~10:30 pm - 1 Sun: 8 pm - 12 am

## Slide 3: Repository and Access
Platform: GitHub
Repository URL:
Instructor invited as viewer? Not Yet, will count as final submission as well
Repo Structure Requirement (summary): Include /docs with pseudocode,
UML/diagram, design notes; keep updated at checkpoint.

## Slide 4: Project Deadlines
Due | Assignment
Oct 11 | Weekly Status Report Week 1
Oct 18 | Weekly Status Report Week 2
Oct 18 | Checkpoint
Oct 25 | Weekly Status Report Week 3
Oct 25 | Peer Review
Oct 25 | Set Operations - Project Due

## Slide 5: Milestones (Timeline)
Target date | Milestone | Definition of Done | Status | Evidence Pointer
Oct 11 | Repo set up + running skeleton | Repo is made & there is a runnable skeleton | D | CS2430-Project-2/src/…
Oct 16 | Core implementation | Required features implemented; compiles | D | CS2430-Project-2/src/…
Oct 18 | Verification (testing) | Edge cases are covered; document actual vs expected results | IP | 
Oct 23 | Report/Video drafts | Report draft done; video outline/script notes | NS | 
Oct 25 | Final integration + submission | All deliverables ready | NS | 

## Slide 6: Task Backlog (Assignments + Status)
ID | Task | Owner | Due Date | Status | Evidence Link/Pointer | Notes/Dependencies
1 | Create Repo (contains runnable skeleton + current implementation branch) | Mustafa |  |  |  | 
2 | UML diagram | Mustafa | 10/18 | D | /docs/proj_1_uml.png | 
3 | Pseudocode | Mustafa | 10/18 | D | /docs/proj_d_pseudocode.md | 
4 | /docs folder with Project Plan and 2 design artifacts | Team | 10/18 | D | /docs/… | 
5 | Verification Plan | Helen | 10/18 | D | /docs/CSIS2430_Project2_Plan | 
6 | Verification Testing | Helen | 10/20 | IP |  | 
7 | Team report |  | 10/23 |  |  | 
8 | Team screencast video (<=10mins) |  | 10/23 |  |  | 
9 | Team code package.zip containing: all src code, README, CONTRIBUTIONS.md, data output files | Owen | 10/25 |  |  | 

## Slide 7: Verification Plan (Verification Lead)
Correctness checks / tests to run
Unit test for core set, multiset, and fuzzy set operations (NOT(A), A ∪ B, A ∩ B, A - B, A ⊕ B).
Verify that Universal set generates with n >= 10 elements.
Verify that the ordinary sets using bit strings/boolean arrays display both bit string/boolean array and element-name listing.
Verify fuzzy sets output as expected with different membership values
Edge cases to verify
Empty set
Sets with no overlapping elements or all identical elements
Multisets with duplicated elements of different sizes
Fuzzy sets: with values 0 and 1; with values in between 0 and 1
3. Expected vs. actual outputs
Bit string/boolean array and element-name are output
Element actual counts match expected counts for multisets
Fuzzy set actual memberships matches expected memberships

## Slide 8: Risks/Blockers
Risk/Blocker | Impact | Mitigation Plan | Owner | Status

## Slide 9: Update Log
Date | Update Summary | Blockers/Resolution | Owner | Evidence Pointers
Oct 4 | Repo created |  | Mustafa | CS2430-Project-2
Oct 11 | UML Diagram made |  | Mustafa | /docs/proj_1_uml.png
Oct 12 | Pseudocode |  | Mustafa | /docs/proj_d_pseudocode.md
 | JUnit tests created |  |  | 
 | Report created |  |  | 
 | Videos made and stitched together |  |  | 
 | Deliverables packaged for submission |  |  |